## Summary
Count of Object | Column Labels
Row Labels | APEX Screen | APEX Templates | OIC | PL/SQL | TABLE | VIEW | Grand Total
CHM --> Oracle Rebate Payment | 2 |  | 2 | 2 |  |  | 6
CHM Reports | 1 | [5 empty] | 1
Enlighten --> CHM | 2 | [5 empty] | 2
Home | 1 | [5 empty] | 1
Master Data Screens | 1 | [5 empty] | 1
ORACLE-->CHM Shipments | 1 |  | 1 |  |  |  | 2
Rebate Payment Approval | 2 | [5 empty] | 2
Rebate Payment Batch Creation | 3 |  |  | 1 |  |  | 4
Rebate Payment Batch Maintenance | 4 | [5 empty] | 4
Rebate Payment Calculation |  |  |  | 3 |  |  | 3
Rebate Payments Inquiry | 1 | [5 empty] | 1
SFDC --> CHM SPA | 5 |  | 1 |  |  |  | 6
SFDC-->CHM Installer | 1 |  | 1 |  |  |  | 2
Supporting Objects |  | 1 |  | 1 | 19 | 6 | 27
Grand Total | 24 | 1 | 5 | 7 | 19 | 6 | 62

## Objects
S.No | JIRA id | Feature | Object | Description | Object Type | Story Points | Developer | Current Dev Status | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09 | 2025-05-16 | 2025-05-23 | 2025-05-30
1 |  | SFDC-->CHM Installer Bank Account Flag | OIC Interface for SFDC--> CHM Installer Master - Bank Detail Flag | Installer Master Bank Detail Flag Sync from CHM-->Fusion | OIC | 8 | Rama | Dev in progress | bar: 2025-02-14 to 2025-02-21
2 |  | SFDC-->CHM Installer | Modify Screen for Installer Master | View Only - Modify Existing Screen | APEX Screen | 2 | Avinash | Dev complete | bar: 2025-02-21
3 |  | ORACLE-->CHM Shipments | OIC Interface for Oracle --> CHM Shipments Data Master (WMS) | Shipment Master Data from CHM --> Fusion | OIC | 13 | Gurpreet | Dev complete | bar: 2025-02-21 to 2025-03-07
4 |  | ORACLE-->CHM Shipments | Screen for Oracle Shipment Details | View Only | APEX Screen | 5 | Avinash/Ronnie | To Do | bar: 2025-02-21 to 2025-02-28
5 |  | Enlighten --> CHM | Screen for Enlighten Site Details (CHM_ENLIGHTEN_SITE_MASTER) - READ ONLY (Master Data) | View Only | APEX Screen | 5 | Avinash/Ronnie | Dev complete | bar: 2025-03-07 to 2025-03-14
6 |  | Enlighten --> CHM | Screen for Enlighten Device Activation Details (show calculations) (CHM_ENLIGHTEN_DEVICE_DETAILS) READ ONLY (Master Data) | View Only | APEX Screen |  | Avinash/Ronnie | Dev complete
7 |  | SFDC --> CHM SPA | OIC Interface for SFDC --> CHM SPA Interface Details | MSI/AVR SPA Master Sync from SFDC --> CHM | OIC | 3 | Gurpreet | To Do | bar: 2025-03-07 to 2025-03-14
8 |  | SFDC --> CHM SPA | Screen for MSI/AVR SPA Header | View Only | APEX Screen | 2 | Avinash/Sohil/Ronnie | To Do | bar: 2025-03-14
9 |  | SFDC --> CHM SPA | Screen for MSI/AVR SPA Additional Distis | View Only | APEX Screen | 2 | Avinash/Sohil/Ronnie | To Do | bar: 2025-03-21
10 |  | SFDC --> CHM SPA | Screen for MSI/AVR SPA Installer Accounts | View Only | APEX Screen | 2 | Avinash/Sohil/Ronnie | To Do | bar: 2025-03-28
11 |  | SFDC --> CHM SPA | Screen for MSI/AVR SPA Rebate Details | View Only | APEX Screen | 2 | Avinash/Sohil/Ronnie | To Do | bar: 2025-04-04
12 |  | SFDC --> CHM SPA | Screen for MSI/AVR SPA Geo Data | View Only | APEX Screen | 2 | Avinash/Sohil/Ronnie | To Do | bar: 2025-04-11
13 |  | Rebate Payment Approval | Screen for Defining Approval Hierarchy | Admin Screen | APEX Screen |  | Sohil | To Do | bar: 2025-04-18
14 |  | Rebate Payment Batch Maintenance | Screen for Payment Batches Header | Transaction Screen | APEX Screen | 13 | Sohil | To Do | bar: 2025-02-21 to 2025-03-07
15 |  | Rebate Payment Batch Maintenance | Screen for Payment Batch Details | Transaction Screen | APEX Screen | 5 | Sohil | To Do | bar: 2025-02-28 to 2025-03-07
16 |  | Rebate Payment Batch Maintenance | Screen for showing Log Messages in Payment Batch Headers | Errors and Exceptions Screen | APEX Screen | 2 | Sohil | To Do | bar: 2025-03-14
17 |  | Rebate Payment Batch Maintenance | Screen for showing Log Messages in Payment Batch Details | Errors and Exceptions Screen | APEX Screen | 2 | Sohil | To Do | bar: 2025-03-21
18 |  | Rebate Payment Batch Creation | Screen for Submitting Payment Batch Creation | Batch Process submission Screen | APEX Screen |  | Sohil | To Do | bar: 2025-02-14 to 2025-03-14; 2025-04-04 to 2025-04-18; 2025-05-09 to 2025-05-30
19 |  | Rebate Payment Batch Creation | Screen for showing Payment Batch Creation Data | Transaction Screen | APEX Screen |  | Sohil | To Do | bar: 2025-02-14 to 2025-04-18; 2025-05-09 to 2025-05-30
20 |  | Rebate Payment Batch Creation | Screen for showing Payment Batch Creation Log Messages | Errors and Exceptions Screen | APEX Screen | 2 | Sohil | To Do | bar: 2025-04-11
21 |  | CHM --> Oracle Rebate Payment | Screen for showing AP Invoice Batch Data | Transaction Screen - View Only | APEX Screen | 5 | Sohil | To Do | bar: 2025-04-11 to 2025-04-18
22 |  | CHM --> Oracle Rebate Payment | Screen for showing AR Credit Memo Batch Data | Transaction Screen - View Only | APEX Screen |  | Sohil | To Do | bar: 2025-02-14 to 2025-04-25; 2025-05-23 to 2025-05-30
23 |  | Home | Home Screen with Cards | Home Screen - View Only | APEX Screen | 13 | Avinash/Sohil | To Do | bar: 2025-02-21 to 2025-03-21
24 |  | Rebate Payment Approval | Screen for Payment Batch Approval | Approval Screen | APEX Screen | 2 | Sohil | To Do | bar: 2025-03-28
25 |  | Rebate Payments Inquiry | Screen to Inquire about Rebate Payments - Query by Filter, Dates, SKU, S/N, Site ID, Country, State, Zip, SPA | Screen to Inquire about Rebate Payments - Query by Filter, Dates, SKU, S/N, Site ID, Country, State, Zip, SPA | APEX Screen |  | Avinash/Sohil | To Do
26 |  | Master Data Screens | New Cards to be added to existing Master Data screen | New Cards to be added to existing Master Data screen | APEX Screen | 5 | Avinash | To Do | bar: 2025-02-21 to 2025-02-28
27 |  | CHM --> Oracle Rebate Payment | OIC Interface to pick AP Invoice data from CHM and send it to Fusion | Take AP Invoice Data from CHM to Fusion | OIC | 5 | Gurpreet/Rama | To Do | bar: 2025-04-18 to 2025-04-25
28 |  | CHM --> Oracle Rebate Payment | OIC Interface to pick AR Credit Memo from CHM and send it to Fusion | Take AR Credit Memo Data from CHM to Fusion | OIC |  | Gurpreet/Rama | To Do | bar: 2025-02-14 to 2025-05-02; 2025-05-23 to 2025-05-30
29 |  | Rebate Payment Calculation | Activation Data Additional Attributes | 1) Derive Disti based on S/N 2) Derive Order Type - Revenue or RMA for the Device based on S/N 3) Derive Effective Date for SPA Eligibility using Site & Activation Dates | PL/SQL | 5 | Raj/Sohil/Ronnie | To Do | bar: 2025-02-28 to 2025-03-07
30 |  | Rebate Payment Calculation | Eligible SPA and Rebate Type Tagging | 1) Derive SPA that the SKU is eligible for 2) Derive if SKU is eligible for Activation Rebate Type 3) Derive if SKU is eligible for System Attachment Rebate Type 4) Derive if SKU is eligible for System Incentive Rebate Type 5) Derive Payee | PL/SQL | 5 | Raj/Sohil/Ronnie | To Do | bar: 2025-03-14 to 2025-03-21
31 |  | Rebate Payment Calculation | Rebate Amount Calculation | For Rebate Eligible Activation Records 1) Calculate Activation Rebate $ 2) Calculate System Attachment Rebate $ 3) Calculate System Incentive Rebate $ | PL/SQL | 21 | Raj/Sohil/Ronnie | To Do | bar: 2025-03-28 to 2025-04-18
32 |  | Rebate Payment Batch Creation | Create Payment Batch | 1) Batch Unpaid Rebate Amounts into Payment Batch 2) Mark the records with status = Pay Batch Created and tag the Payment Batch Number | PL/SQL | 13 | Raj/Sohil/Ronnie | To Do | bar: 2025-04-04 to 2025-04-18
33 |  | CHM --> Oracle Rebate Payment | Create AP Invoice | 1) All Apporved Payment Batch Lines will be grouped into AP Invoices | PL/SQL | 2 | Raj/Sohil/Ronnie | To Do | bar: 2025-04-18
34 |  | CHM --> Oracle Rebate Payment | Create AR Credit Memo | 1) All Apporved Payment Batch Lines will be grouped into AR Credit Memo | PL/SQL |  | Raj/Sohil/Ronnie | To Do | bar: 2025-04-25
35 |  | CHM Reports | Interactive Report for Rebate Payments Data | Report Screens | APEX Screen | 21 | Avinash/Ronnie | To Do | bar: 2025-04-11 to 2025-05-02
36 |  | Supporting Objects | Utilities Package |  | PL/SQL | 21 | Ronnie | To Do | bar: 2025-02-14 to 2025-04-04
37 |  | Supporting Objects | Email Templates for Error Reporting | Email Templates | APEX Templates | 8 | Avinash | To Do
38 |  | Supporting Objects | ENLIGHTEN SITES table | Populated by Boomi Process | TABLE | 2 | Ronnie | Dev complete | bar: 2025-02-14
39 |  | Supporting Objects | ENLIGHTEN DEVICE data | Populated by Boomi Process | TABLE | 2 | Ronnie | Dev complete | bar: 2025-02-14
40 |  | Supporting Objects | MSI/AVR SPA Header Data | Populated by OIC Interface | TABLE | 2 | Ronnie | Dev complete | bar: 2025-02-21
41 |  | Supporting Objects | MSI/AVR SPA Additional Distis | Populated by OIC Interface | TABLE | 2 | Ronnie | Dev complete | bar: 2025-02-21
42 |  | Supporting Objects | MSI/AVR SPA Activation Rebate Data | Populated by OIC Interface | TABLE | 2 | Ronnie | Dev complete | bar: 2025-02-21
43 |  | Supporting Objects | MSI/AVR SPA System Attachment Rebate Data | Populated by OIC Interface | TABLE | 2 | Ronnie | Dev complete | bar: 2025-02-21
44 |  | Supporting Objects | MSI/AVR SPA System Incentive SKU Data | Populated by OIC Interface | TABLE | 2 | Ronnie | Dev complete | bar: 2025-02-21
45 |  | Supporting Objects | MSI/AVR SPA System Incentive SKU <--> Tier Rebate Data | Populated by OIC Interface | TABLE | 2 | Ronnie | Dev complete | bar: 2025-02-21
46 |  | Supporting Objects | MSI/AVR SPA Geo Data | Populated by OIC Interface | TABLE | 2 | Ronnie | Dev complete | bar: 2025-02-21
47 |  | Supporting Objects | MSI/AVR SPA Installer Data (Parent & Child Accounts) | Populated by OIC Interface | TABLE | 2 | Ronnie | Dev complete | bar: 2025-02-21
48 |  | Supporting Objects | DEVICE Additional Attributes Data | Populated by PLSQL Batch Process - Activation Data Alternate Attributes | TABLE | 2 | Ronnie | Dev complete | bar: 2025-02-14
49 |  | Supporting Objects | DEVICE Rebate Amounts Detail | Populated by PLSQL Batch Process - Eligible SPA and Rebate Type Tagging | TABLE | 2 | Ronnie | Dev complete | bar: 2025-02-14
50 |  | Supporting Objects | AP Invoice Data | Populated by PLSQL Batch Process - Create AP Invoice | TABLE | 8 | Ronnie | To Do
51 |  | Supporting Objects | AR Credit Memo Data | Populated by PLSQL Batch Process - Create AR Credit Memo | TABLE |  | Ronnie | To Do
54 |  | Supporting Objects | Batch Approval Details | Populated from APEX Screen when batch is Approved or Rejected | TABLE | 2 | Ronnie | To Do
55 |  | Supporting Objects | Alternate SKUs Master | Populated by users using APEX Screen (User uploads Data) | TABLE | 2 | Ronnie | To Do
56 |  | Supporting Objects | Debug log Table | Debug log Table | TABLE | 2 | Ronnie | Dev complete | bar: 2025-02-14
57 |  | Supporting Objects | View for SPA Details | View for SPA Details | VIEW | 2 | Raj/Ronnie | Dev in progress
58 |  | Supporting Objects | View for Payment Details | View for Payment Details | VIEW | 2 | Raj/Ronnie | To Do
59 |  | Supporting Objects | View for Shipment Details | View for Payment Details | VIEW | 2 | Raj/Ronnie | To Do
60 |  | Supporting Objects | View for Enlighten Site Details | View for Payment Details | VIEW | 2 | Raj/Ronnie | To Do
61 |  | Supporting Objects | View for Enlighten Device Activation Details | View for Payment Details | VIEW | 2 | Raj/Ronnie | To Do
62 |  | Supporting Objects | View for SPA Additional Disti Details | View for SPA Additional Disti Details | VIEW | 2 | Raj/Ronnie | Dev in progress
63 |  | Enlighten --> CHM | Bring Enlighten Site & Device Activation Details into CHM | Bring Enlighten Site & Device Activation Details into CHM | BOOMI |  | Harisha (Enphase) | To Do
64 |  | Enlighten --> SFDC | Installer Bank Details Submitted Flag attribute from Enligthen to SFDC | Installer Bank Details Submitted Flag attribute from Enligthen to SFDC | BOOMI |  | Harisha (Enphase) | To Do
65 |  | Enlighten --> Oracle Vendor Creation | Create Vendor and Bank Account Details in Oracle AP | Create Vendor and Bank Account Details in Oracle AP | RPA |  | Vamshi (Enphase) | To Do
66 |  | Enlighten --> Oracle Vendor Creation | Create Vendor and Bank Account Details in Oracle AP | Create Vendor and Bank Account Details in Oracle AP | OIC |  | Harisha / Gurpreet | To Do
67 |  | CHM --> Incorta Integration | Send MSI & Rebate Payment Details to Incorta | Send MSI & Rebate Payment Details to Incorta | Incorta |  | Syed (Enphase) | To Do
68 |  | Manual Payment Batch (Excel Upload) | Manual Payment Batch (Excel Upload) | Manual Payment Batch (Excel Upload) | APEX Screen |  | Anirudh(Enphase) | To Do
[5 empty] | Total | 246
|  | Status | % Alloted
|  | To Do | 0%
|  | Analysis in progress | 5%
|  | Dev in progress | 15%
|  | Dev complete | 70%
|  | Unit Test Completion | 90%
|  | QA completion | 100%